Massachusetts DPU 11-75: Distributed Generation Interconnection Standards

Draft Final Report from DG Working Group to Department

Drafted by Dr. Jonathan Raab, Raab Associates (DG WG Facilitator)

REVISED August 31, 2012

NOTE: Text highlighted in Yellow designated still unresolved issues; and text highlighted in Blue—largely just new text for your review.

Cover Letter from Facilitator (Provided prior to 10th/11th mtg.)

List of Organizations (Representative/Alternates/Others) Endorsing the Report (submit active representative and alternate organizations on 11th, Give other participants and interested parties a week to join in support of consensus recommendations and subscribe to any options  in report where no agreement.  Can’t offer alternative options, dissents, etc.—those would have to be during DPU formal process.  Facilitator consolidates list and submits to DPU)

Table of Contents

Section 1: Introduction, Background, and Overview

(To Be Sent For Your Review By Tuesday)

Section 2: Application Review Process: Tracks and Revised Screens

The Working Group recommends changing several screens in the Simplified and Expedited tracks as well as increasing the number of engineering review hours within the Expedited track with the express purpose of allowing more projects to remain in these tracks and hence move more rapidly through the interconnectin process.  The Working Group also recommends additional time for more complex projects within the Standard track.  Lastly, the Working Group recommends the addition of a Group (aka Cluster) track for multiple applications on feeders that are relatively saturated with distributed generation such that very expensive upgrades would be necessary.  The Group track would allow the utility to study multiple projects at once and establishes study and construction cost allocation approach

- Simplified Track

Consider increasing 10 KW single phase and 25 KW three phase screen?  Can we increase size but then have them cover upgrade costs.

- Simplified and Expedited Track/Screen #2

The Working Group recommends changing one of the existing screens (Is the aggregate generating Facility capacity on the circuit less than 7.5% of circuit annual peak load?) to potentially allow more DG thru the Simplified and Expedited tracks, as follows: Is the aggregate generating Facility capacity 15% of feeder/circuit and, if available, line segment?

- Simplified Spot Network Track/Screens

Utilities are studying area networks to develop the data needed to come up with appropriate/safe screens for area networks. For now, the Working Group recommends that the simplified spot network screens also apply to area networks (if other screens are passed) as long as applicant has interval meter data for an appropriate time period, and where available minimum load data, for area networks. The Working Group further recommends removing the requirement that the system be less than or equal to 15 kw, as long as the less than 1/15 of Customer’s minimum load is met.  The Working Group also recommends continuing to monitor and track IEEE 1547 and national best practices and for the Massachusetts utilities to continue to study and experiment on area networks (e.g., NSTAR pilot project).  They further recommend incorporating networks and IEEE handling of networks into new technical upgrade criteria and standards manual discussed in Section X.

- Expedited Track Screens

The Working Group recommends adjusting the Expedited track screens to allow more applications to remain in the Expedited track instead of going through the longer Standard track.  Specifically the Working Group recommends adding three Supplemental Review screens to the interconnection process:

- Penetration Test

- Power Quality and Voltage Tests

- Safety and Reliability Tests

Specifically, the Working Group agrees to define and implement the Power Quality and Voltage Tests and Safety and Reliability Tests screens based on the California tests as follows:

Add the Language Supplied by DG Cluster (and remove CA language below):

For the Penetration Test (aka minimum load screen), the Working Group is still discussing two options, a) the California/NREL approach based on whether the aggregate Generating Facility capacity on the Line Section is less than 100% of the minimum load for all the line sections bounded by the automatic sectionalizing devices upstream of the Generating Facility; or b) the Sandia Labs 67% minimum load screen.

- 100% Screen--Add language from DG Cluster

- 67% Screen—Add language from Utility Cluster (Use of a 67% minimum load screen(Where minimum load values are available) as part of the supplemental review as well as the other proposed supplemental review screens - a recent Sandia Labs report has suggested this is the appropriate percentage of minimum load to use, An important caveat, again explained in the report, is that this screen can not be used if there is a mix of non-homogeneous inverters or other types of DG elsewhere on site or on the feeder (report has been sent around previously and/or can be provided on request.)

Group Discussion Notes:

- Sandia 67% screen packaged with other screens that make it behave closer to 100% minimum load screen.

- Main concern of 100% is potential for anti-islanding.  Can we add an anti-islanding screen(s) and use 100%?

The Working Group also recommends raising the Supplemental Review time allowed within the Expedited track from 10 hours to 30 hours.  Thus projects would be allowed to stay in the Expedited track and not sent to the Standard track if more than 10 hours of engineering review time is required.

- Complex Projects Within Standard Track

The Working Group discussed at length how to handle the increase of complex projects or projects seeking interconnection at challenging locations that require more studies and study time than initially contemplated when the Standard track and its timelines were designed.  The Working Group agreed to maintain the Standard Track, but to allow for additional utility review time in certain circumstances.  See Section 3 for details.

- Accelerating Interconnection Agreement Signing

The Working Group recommends adding language to the tariff that allows applicants to request and sign an Interconnection Agreement at the end of the Impact Study rather than waiting until after the Detailed Study.  If the applicant goes with this option they agree to accept the +/-25% construction cost estimates emanating from the Impact Study.  They also will have to wait for a detailed construction schedule until after the utility completes its design engineering work (as discussed in Section X under construction timelines).

- Group (aka Cluster) Study

The Working Group recommends that that a new Group (aka Cluster) Study process should be required on feeders where capacity is “exhausted ” (technically infeasible to operate on a single distribution feeder, e.g., Grid’s 3 MW PV on a 15 KV line 5 MW on 25 KV line) (or near exhausted), or where new express feeder is needed, or both.   The Group study would also be optional in other circumstances identified by utilities as potential good candidates for Group studies, or proposed by applicants.

- Required Group Study Process

  - Utility decides when application triggers exhausted feeder, and  Option 1: that opens up group study window; Option 2: next applicant has option to proceed on own or move to group study]

  - Group study process is then required for all applicants wishing to interconnect on the feeder

  - Open enrollment window for 3 months

  - Timeline for utility: Option 1: mutually agreed to timeframes; Option 2: Complex study timeline, or mutually agreed to

  - Must follow cost allocation rules for Group studies (recommended by Working Group in Section X of this Report)

- Optional Group Study Options

  - Optional in other circumstances if applicants come together and propose to utility, or utility identifies other areas where Group studies may benefit applicants

Section 3: Application and Construction Timelines

In this section the Working Group recommends changes to timelines for Complex projects within the existing Standard Track and timelines for the new Group study process.  It also recommends clarifying language and some modifications to the related to witness test and construction timelines, as well as new language regarding force majeure.  [Add Simplified reference if changes.]

- Simplified Track

Option 1: The Working Group does not propose any changes to the timelines in the Simplified process for now, but will consider reducing the 15 day total maximum day once the online application process is up and running and the utilities are fully staffed up.

Option 2: Working Group recommends reducing the total maximum days from 15 days to 10-12? once the new online application process is in place

- Expedited Track

The Working Group does not propose any changes to the Expedited timelines, except to clarify the timing in the Witness Test (see below in this section).

- Complex Projects in Standard Track

The Working Group recommends adding additional time within the Standard review track for complex projects or projects proposing to interconnect in challenging places.  These types of projects typically require more expensive system upgrades that necessitate more study time than Standard track timelines afford.  Therefore for these types of projects or situations the Working Group recommends:

- If any Sub-Station modifications are needed—Add a maximum of 20 days business days for utility to complete the Impact Study

- If system modifications from the Impact Study indicate likely to cost over $100,000 for system and substation upgrades (but excluding any on-site-at point of interconnection- service related costs)—Add a maximum of 45 days for Detailed Study

  - Alternative for #2:  Add 45 days for substation upgrades, or 20 days for distribution system upgrades only

- Utilities will inform applicants within 20 days into Impact study whether 1, 2, or both time extensions are needed

- Group (aka Cluster) Study

The Working Group recommends that where a Group study is implemented whether required by utilities or voluntary the study timeframe should be by mutual agreement between the utility and the Group members.  [Another alternative would be to follow guidelines in Standard Process for Complex projects?]

- Construction Timelines

The Working Group recommends that there should continue to be clear construction timelines w/milestones included in the Interconnection Agreement (except in the case where Applicant requests an Interconnection Agreement after the Impact Study and before a Detailed Study, in which case the construction schedule is added after the utility completes its design engineering).  They further recommend the timelines be tracked using a chess clock just as with the interconnection agreement steps.  While the Working Group recognizes that there are many reasons that construction schedules may slip on both the applicant and utility side, milestones should only be missed for reasonable cause.

If a utility misses a milestone it will inform both the applicant and the DPU including the reason and a proposed new schedule.  If the customer misses a milestone, the utility will follow the same protocols for Customer Adherence to time schedules described below in Section 7.

The Working Group also recommends that construction time guidelines for different upgrade costs and timeframes be included in the Technical Manual referenced in the tariff, and periodically updated, with stakeholder   input and review (see below for illustrative example—note if multiple upgrades required some can be done concurrently so timelines not necessarily addititive).

- Force Majeure

The Working Group recommends that for force majeure (e.g., major storms, strikes, war, extreme heat event,,or other significant interruption in utility DG workforce) that the chess clock would be stopped for that period (for the utility, customer, or both depending on who’s impacted by the force majeure). There should be notice when force majeure events occur (potentially through the independent administrator). Volume of applications would not be force majeure. [Delete language in tariff about complying with timelines only under “normal work conditions”].

If there is a major (and abrupt) change in State or Federal policy or DG price change that prompts significant and rapid increase in applications.  Utilities will use best efforts to adjust (human) staffing/resources to handle the new application volume within the tariffed time lines.  If they can’t staff up rapidly enough to meet the timelines, they will let the DPU know and file a plan to meet the deadlines as expeditiously as possible.  Utilities and DG related stakeholders will work together to anticipate these types of changes, and minimize their impacts on the interconnection process.

- Witness Test

- Simplified: Leave Language as is Section 3.1 (Item F)

- Expeditid: Add new section for Expeditied—Identical Language as Simplified

- Standard: (Replace Section 3.3.3.B.i with the following) The Company will require a witness test of the Facility for compliance with the relay settings as approved by the Company. The Interconnecting Customer will provide a proposed witness test and the requisite supporting documentation for review by the Company once they have completed the installation of the facility. Utility will have 5/10 business days to approve the witness test once they have all the information needed from the Customer.  The utility will then inform the Customer when they have approved test procedures. Once the test has been approved by the Company, the Interconnecting Customer will call to arrange for the Witness Test. The Interconnecting Customer has no right to operate in parallel until a Witness Test has been passed. The Company is obligated to complete this Witness Test within 10 business days or by mutual agreement upon receipt of the request for a witness test as outlined above.

Section 4: Adherence to Utility and Applicant Timelines

In this section the Working Group recommends strategies and requirements to enhance adherence to timelines during the application and construction phases of distributed generation interconnection—on both the applicant/customer and utility sides.

- Applicant/Customer Adherence (aka Stale Project Management)

The Working Group recognizes the need to remove stale projects that have exceeded their timelines to provide utilities with requested information or decisions to proceed.  Stale projects can hold up other projects behind them in a queue on a particular feeder.  However, even when there is not a queue, stale projects still require utility tracking and periodic attention, and also can give the misconception that many projects are actively awaiting interconnection.  For all these reasons, the Working Group proposes a process that includes an initial withdrawal of stale projects, as well as an on-going customer timeline compliance process to deal with applicants who miss their deadlines, as outlined below.

- Initial Withdrawal

  - For all applicants where the utility is waiting to hear from the customer at any level at any stage (in application and construction process) for more than 30 business days

  - Utility contacts applicant (email and letter and/or phone if no email address)—customer of record, alternative contact, and a most recent point of contact

  - “Haven’t heard from you in over 30 business days, if don’t hear from you in 30 business days, we will consider your application withdrawn (and if you want to continue at a later date, you will need to reapply).”  Any fees not refunded.

  - (Indicate removal being required by DPU)

  - Utilities already have the authority in the original tariff—“may” remove from queue

- On-Going Customer Timeline Compliance (for all projects whether in a queue or not)

  - Request from utility to applicant for information or signature will include customer deadline from tariff

  - If miss deadline, send email that missed deadline and will be given 3 business days to cure or request an extension

  - If request extension, granted one extension equal to timeline/deadline of step (Open Questions:

    - Should there be only one extension during course of interconnection application process or allow one extension at each different stage;

    - Should there be longer-time line extensions for public projects or particular technologies with or without cause? (see net metering assurance language for cause)

    - Should applicants be required to $ at certaint steps to remain in process if customer delays?

  - Utilities need to keep track of extension dates

  - Projects that don’t meet extended timelines considered withdrawn, need to reapply

  - Customers will have 20 business days to sign an Interconnection Agreement by the utility or provide comments to the utility on the IA, or the project will be considered withdrawn and will need to reapply.  If customer provides comments, the customer and the utility will have 30 business days to resolve.  After 30 days, if no resolution and no request from the customer for ADR, the application will be considered withdrawn and need to reapply.

- Timeline (after DPU approval)

  - Initial Withdrawal—Begin right after DPU approval (2-3 months to complete)

  - On-Going Customer Timeline Compliance—Concurrently w/Initial withdrawl or after/sequential?

- Utility Adherence (aka Assurance and Enforcement) to Timelines

The Working Group recommends the following suite of measures to ensure and enforce utility compliance with tariff timelines.

(Note to WG: I put the current proposal from utilities up front, but left other material in section for reference for now.  Will delete extraneous stuff later.

Utilities Are willing to negotiate following:

- Refunding application fees for Expedited and Standard processes when timelines are missed

- Expedited process at DPU/ADR process/Ombudsperson (more toward engineering side)

- Give DG access to outside engineers/contractors to conduct studies and do construction if utilities anticipate not meeting timelines (need to think thru this more)

- If deadline missed will inform DPU and customer including reason and proposed revised timeline

- Service quality metric approach for DG either as part of the existing SQ metrics or free-standing metric open for discussion (but premature to institute or finalize details)

DG et al Response:

- Anything comparable to refund application fees for those in Simplified track if deadlines missed, where currently no fee?—shorter timeline 15 days to 10 days?

- Package of 5 possible utility proposals possible package depending on details

  - Need to develop language for report that lays out a service quality process and timeline--Reid

  - Develop report language with more specificity for A-D—Utilities and Non-Utilities

  - Consider whether anything else should be added to list

  - Develop a transition strategy

Principles for consideration:

  - Let utilities also be allowed to have timelines slip in certain clear circumstances for good cause

  - Focus on enforcement mechanisms first that have both incentives/offsets and disincentives, rather than just disincentives

  - Need a functional chess clock to base enforcement on

# Metric Definition and Calculation

The new metric would be called the Distributed Generation Application Days Index (DGADI), and would be calculated using the following formula:

Where:

= 	Number of Expedited applications received in the calendar year

= 	Number of Standard applications received in the calendar year

= 	Average number of days between “Date Application Deemed Complete” and “Date Interconnection Agreement Sent” for projects in the Expedited process.

= 	Average number of days between “Date Application Deemed Complete” and “Date Interconnection Agreement Sent” for projects in the Standard process.

# Integration with Existing Service Quality Plans

It is intended that a DG interconnection-related metric would function identically to other Service Quality metrics, as defined by the DPU.  This includes the calculations of benchmarks, penalties, and offsets.  Because those calculations are defined in each utilities Service Quality Plan, they will not be presented here.

The current Service Quality Plans for each utility allow the utility to be fined for a maximum of 2.5% of the company’s annual transmission and distribution revenue.  Penalties and offsets for all Service Quality metrics are then allocated within this 2.5%.  The table below shows the current allocation versus the proposed allocation.

| SQ Metrics | Existing | Proposed |
| --- | --- | --- |
| Measure Penalty | Percentage | Percentage |
| SAIDI | 22.50% | 22.50% |
| SAIFI | 22.50% | 22.50% |
| CKAIDI * | 11.25% | 11.25% |
| CKAIFI * | 11.25% | 11.25% |
| Telephone Answering (20 Sec) | 12.50% | 10.00% |
| Service Appointments | 12.50% | 10.00% |
| Lost Work Time Rate | 10.00% | 10.00% |
| On-cycle Meter Reads | 10.00% | 10.00% |
| Consumer Division Cases | 5.00% | 5.00% |
| Billing Adjustments | 5.00% | 5.00% |
| DG Application Days | 0.00% | 5.00% |
| TOTAL | 100.00% | 100.00% |
| * Only if the Company is not subject to SAIDI or SAIFI penalty in a given year. |

  - Comments From Group Discussion

    - Data set used in analysis doesn’t include projects still in queue

    - Should this be part of existing service quality metrics, or a stand-alone service quality metric?

    - Existing service quality metrics designed more for all ratepayers than narrow groups of customers

- DOER drafted approach for discussion

- Enforcement

  - Project Basis

    - Upon failure to meet the timelines, the Utility shall promptly refund the application fee and study costs to the customer.

    - For each full 20 business days that the Utility remains in breach of the timelines, the Utility shall pay $50/kW to the customer in compensatory damages.

  - Annual Review

    - If greater than 10% of projects exceed timelines, the Utility shall pay a penalty of $50/kW of projects exceeding timelines.

    - Annual Review penalties shall be paid to the Massachusetts Clean Energy Council (“MassCEC”). Such funds shall be held in an account separate from other accounts of the MassCEC. DOER shall oversee the use of Annual Review penalty funds by the MassCEC, so as to address interconnection streamlining, including but not limited to staffing assistance.

  - No Ratepayer Recovery

- The payments described under this section shall not be recoverable through ratepayers.

Utility Feedback on DOER Penalty (Death penalty vs. speeding tickets)

- Penalties should be last recourse

- Due process before penalties applied

- High hurdle before applied

- Case by case basis

- Tailor penalty to specific problems

- Premature for penalties

- ADR process first, then can ask for penalties

- Not confident chess clock can be basis for penalties

- Need adjudicated venue to determine penalties

- Still discussing w/service quality is better way to go, but don’t have long-term data

Section 5:  Fees

The Working Group recommends updating the fees for the Expedited and Standard processes to account for actual labor rates and anticipated review times. We also lay out cost allocation approach for new Group study process.  Actual costs will still be charged for Impact Studies and Detailed Studies. [Add language about Simplified and O&M if have recommendation.]

- Required Pre-Application Report Fees (Expedited/Standard Track Only)

The Working Group recommends that there be no fee for Pre-Application Report, but that the anticipated cost was taken into account when setting the new application fees for the Expedited and Standard processes.

- Simplified Track

The Working Group assumes that the current time to review Simplified applications (now in the 4-8 hour range) will be reduced somewhat with the commencement of a Statewide Application and Tracking system, and recommends that there continue to not be an application fee for applications in the Simplified track. (Note: Does not appear to be a lot of support for a fee here except for one utility and possibly the AG.)

If don’t charge Simplified application needs to be picked up by other DG applicants or all ratepayers

- Expedited and Standard Tracks

Supplemental Review engineering hours raised to utlity average rate w/overhead—from $125/hour (set in 2003) to $150/hour.  (Discuss escalation over time issue.)

Utilities will circulate specific proposal for updated numbers prior to 9/5 meeting.

- Group (Cluster) Study and Upgrade Cost Allocation (repeated from Section 6)

The Working Group recommends that the cost allocation for study and upgrade costs when a group (cluster) study is either required by the utility or a voluntary group (cluster) is established should be as follows:

- Study Cost Allocation—by MW

- Upgrade Cost Allocation

  - Lines—Share common segments pro rata by MW, unique segments covered by that DG provider

  - Other equipment—Share common upgrades pro rata by MW, unique upgrades by that DG provider

  - If one or more DG applicant drops out, then remaining applicant share any additional restudies required

  - If new DG added to circuit within 5 years, need to share costs from prior DG (consistent w/utility line extension policy) (those applicants through the Simplified process would be exempted from this requirement)

- Operation and Maintenance Costs

The utility proposes recovering O&M for large upgrades (e.g., over $75k).  For Grid the 2011 O&M on capital investments (“direct assign facilities”) was 10.91%.  The O&M charge would not be assesses to existing DG customers (online and in application process or just online?) Not retroactive.  If new customers added, in theory reduce their direct assign facilities.  Is this better treated thru rates (DG rate)?

Section 6: Pre-Application Report Requirements

The Working Group recommends adding a new required Pre-Application Report for all applicants going through the Expedited and Standard Tracks.  The intent of this Report is to provide applicants with some basic information about the location at which they are potentially interested in connecting to the distribution system, so that they can get an initial sense of whether the particular location is practical for their project.  The pre-application report could also help applicants prioritize among various locations and possible distributed generation configurations they are considering.  The Working Group believes that this could minimize the number of speculative applications, and increase the likelihood of viable applications.

The pre-application report request would be handled through the proposed new statewide online application and tracking system and then routed to the appropriate utility.  Utilities would have 10 business days to provide the pre-application report.  There would be no fee for this service (however costs reflected in application fees).  Applicants would not be able to submit their actual application in the Expedited and Standard Tracks until a pre-application report is received.

Each Pre-Application Report will carry the following disclaimer: “Be aware that this Report is simply a snapshot in time and is non-binding, system conditions can and do change frequently.”

Applicants would need to provide the following information to the utility through the statewide online application and tracking system:

- Project Contact Information

Name:

Address:

Phone:

Email:

- Location (street address with nearby cross streets, town):

- Generation Type: (solar, wind, CHP)

- Size (AC kWs):

- Single or three phase generator  configuration:

- Stand-alone (no on-site load – Y or N):

- If existing service include customer account number, site minimum and maximum (if available) current or proposed electric loads in kWs

- New service needed?

The “Pre-Application Report” provided by the utility will include the following.

- Circuit voltage:

- Circuit name:

- Voltage at proposed location:

- Single or three phase available near site:

- If single phase – distance from three phase service:

- Aggregate connected  DG (kw) on circuit:

- Submitted complete applications of DG (kw) on circuit that have not yet been interconnected:

- Area network, or spot network or radial:

- Snap-shot within ¼ mile (or otherwise identify feeders within ¼ mile)

- Other potential constraints or critical items that may jeopardize project

Section 7:  Online Application and Information Tracking System

The Working Group recommends the creation of a new centralized application and tracking system (CATS) for distributed generation interconnection project applications in Massachusetts.  This online database would serve as the gateway for applications for distributed generation in all tracks.  It would also serve as a tracking and chess clock for each application from its pre-application submittal through construction.  The Working Group further recommends that CATS is designed, developed, and maintained by an independent third party administrator selected through through an RFP process. Below is an outline of the purpose, inputs, outputs, schedule, and overall strategy agreed to by the Working Group:

- Purpose

  - Centralized Application process

    - Pre-application Report for Expedited and Standard tracks

    - Application--Centralized/Standard application process for all 3 tracks (update interconnections applications)

  - Tracking system (transparency)

    - Individual Applications--Utilities and applicants to know where they are in process and deadlines on a particular application through construction (time stamps on steps been thru)

    - Aggregate Applications--To be able to monitor in aggregate timeline compliance (customer & utility) for everyone including regulators

  - Prospecting—Allow developers to see level of activity on specific feeders, (and whether there’s a group (cluster) study on a particular feeder?)

- Inputs

  - Customer: Completed application

    - (Pre-application Report required information (for Expedited and Standard tracks)

    - Basic information about application (for all Tracks but differs by Track)

    - Automated Application Completeness Check (with checklist)

  - Utility

    - Track applicant is in (Standard (including any additional time allowed for more Complex projects), Expedited, Simplified, Group Study)

    - Additional information about application (screens passed (phase II—as attached document?), construction timelines/milestones)

    - Communications to customers (where applicant is in process, and time stamps)

    - Point of contact (by stage) at utility and customer

- Outputs

  - Completed pre-application and application back to utility

  - Chess clock (Utility and Applicant)

  - ID step where a particular application is  in interconnection review process

  - Show Deadlines for individual applications

  - Ability to sort by feeder (allow developers to sort by feeder to see activity there) and other aggregated sorts

- Schedule (From after DPU Approves Concept)

  - Continue to draft RFP, and ID potential consultants (including the Net Metering Assurances Administrator)

  - Release RFP (either MA CEC or DOER would administer RFP process

  - Consultant Selected—2 Months

  - Consultant work—3 Months

    - Design application and tracking processes

    - Design interface strategy with each utility system (both for utility to update central record, and for utilities to get completed application from central system)

    - Design access and security protocols

    - Schedule and Phasing in strategy

    - On-going cost to run systems

  - DPU Approval (Is this really needed?)—1 Month

  - Administrator Develops, Starts, and, Maintains System (as proposed by consultant)

    - New applications

    - Existing applications (see #5 below)

    - Offer separate Technical support for applicants

- Strategy for Dealing w/Projects Already in Queue

  - Use data from monthly reporting spreadsheet for initial population ( after do stale project withdrawl first)

  - When utilities next touch application, provide step in process and time stamp

- Cost Recovery

  - Design and start up thru ACP

  - Ongoing costs by applicants/hosts rolled into application fees (how set new application fees now to account for this?)

  - No retroactive assessment of applicants in process or on-line

- Overaraching Concerns/Principles

  - Minimize data entry, and avoid double data entry

  - Get tracking clock in place and ticking as fast as possible

- Questions:

  - Can we use net meter assurance administrator?

- Other

  - Training—utilities and applicants for using the new system.  Verification/certification for going thru training

  - What’s public info (comparable to DOER spreadsheet w/feeder info.), and what’s only accessible to applicant/utility?

  - Interim time-clock related strategy—Communicate to customers that utility clock has stopped and ball in your court (with time stamp), and utility clock starting—no tracking—DG HW

Section 8: Other Technical Issues (including Upgrade Criteria and Standards Manual)

- Upgrade Criteria and Standards Manual

The Working Group recommends that utilities develop and make available upgrade criteria and standards manuals based on National Grid’s “ESB-756C”, with the following recommendations:

  - Add information on  infrastructure/system modifications upgrade criteria to manual including costs/timelines and triggers

  - Update manual on an as needed basis with maximum of 3 or 5 years w/stakeholders (DG providers, state agencies, customers) input

  - Option 1: One statewide manual, even if has to be some differences within that document among the utilities Option 2: Each utility has own manual—but structure and content as close as possible

  - Meet semi-annually to discuss with stakeholders new technology, criteria and standards

  - Tariff language referencing manual, and discussing update process—consult w/stakeholders, utilities decide criteria/standards

As part of the transition effort, utilities will compare their standards w/GRID’s and have process laid out including schedule for developing manual(s)

Section 9: Other Issues (ADR, Ombudsperson, Applicant Training/Certification)

ADR Process

The Working Group does not recommend any changes to the current ADR process, which has been largely untested over the past decade.

Ombudsperson

The Working Group is considering recommending on Ombudsperson, details not specified.

Training/Certification

The Working Group is recommending changing the monthly “briefing” into more of a “training” that may or may not include some form of applicant certification. The trainings would provide an opportunity for applicants and utilities to interact, and could be a mandatory part of the application process. This could also link into an online application process that requires applicants to take and pass a “how to apply for interconnection” test before submitting the online application.  Details still need to be worked out.

Section 10: Transition Strategy and On-Going Collaboration

Working Group is recommending the following transition strategy and on-going collaboration to assist in the implementation of the recommendations in this Report.

WE NEED TO DISCUS THIS AND WRITE THIS SECTION

Adding Feeder Info to Monthly Utility Report

The Working Group recommends adding additional information to the utilities monthly reporting to DOER, as an interim measure prior to implementation of the Statewide Online Application and Tracking System.  Sequencing for populating the monthly reporting tracking spreadsheet with feeder identification information is as follows:

- All new complete applications (all tracks)—once utility knows the correct feeder, the number will appear in the report approximately 1 Month after— Starting with the August 2012  report

- All existing projects utilities touch—Starting August 2012 report

- All projects (in process or with authorization to interconnect) over 1 MW—for October 2012 report

(Note: No Timelines yet for the following (which could become moot once centralized tracking system is up and working.)

- All projects with authorization to interconnect (Expedited/Standard)  (October ??)

- All Standard projects

- All Expedited projects

- All Simplified Projects (not reported in monthly reporting at all now)

The Working Group also notes that NSTAR has voluntarily added two other columns to their monthly reporting: 1) Municipal, C/I, residential designation; and 2) Date they asked applicant for additional info.  The Group agreed that the new feeder number field should be three columns from the end of the existing report, so allow DOER to easily integrate the spreadsheets from all utilities.

Geographic Mapping

Add to list of things to work on post-Sept over next year?—accessible geographic mapping that will show feeders/circuits and DG activity (including names of sub-stations, circuits served)

Appendices

Appendix A: Working Group Membership and Participation

Appendix B: Redlined Interconnection Tariff (Is this achievable by 9/11?—Or List of Tariff Changes)

Appendix C: Outline of RFP for Online Application and Information Tracking System Consultant—DELETE/NOT READY

Note: Emphasis in report will be on recommended changes to existing processes and tariff, and won’t need to restate everything else that will remain unchanged.  “New” and “Revised” designation just for WG review--won’t necessarily be in final report.