Massachusetts Distributed Generation Working Group

Interconnection Pre-Application and Feasibility Study Recommendations

# Pre-Application Process

## General Information

A Pre-Application will be required for all proposed projects.

There will be no costs to the developer for a Pre-Application.

All information provided by the utility is non-binding and considered to be for reference purposes only.

## Required Information from Applicant:

Contact information

Proposed location (address and Google map)

Type of DG (solar, wind, CHP)

Size(s)

Exporting on non-exporting

New electric service or existing service

## Information provided by utility:

- Feeder voltage

Voltage at proposed location

Single or three-phase

If single-phase, how far away is three-phase?

How much DG on circuit (connected and proposed)

Substation name, feeder number/designation

Radial, area network, or spot network

Distance to sub-station

Line section upstream protective device

# Feasibility Study

## General Information

Generally, the Feasibility Study would be performed by the utility at the developer’s discretion and would not be required for projects that export 5 MW or less.  For projects exporting more than 5 MW, the Feasibility Study would be required.

The Feasibility Study shall be performed prior to the submission of a full application.

The information required by the utility should be the same as the info that is required for a Pre-Application.

The Feasibility Application should be considered as a simple “up-charge” from the current Screening Memos that are provided by some utilities.

All information and estimates provided by the utility are non-binding and considered to be for reference purposes only.

## Fees

A study fee would be incurred by applicants that opt to have a Feasibility Study performed.

Non-exporting facilities:  $250

Projects exporting 1 MW or less:  $1,000

Projects exporting 1 MW to 5 MW:  $2,500

Projects exporting over 5 MW:  $4,000

## Required Information from Applicant:

- Contact information

Proposed location (address and Google map)

Type of DG (solar, wind, CHP)

Size(s)

Exporting on non-exporting

New electric service or existing service

## Information provided by utility:

- Compliance review of existing screens and determination of appropriate project track

Peak load on proposed feeder

Size and type of DG on feeder (connected and proposed)

Electrical dependence on other proposed projects

Rated feeder capacity and peak load

Major distribution line equipment upstream from proposed feeder location

Reclosers

Capacitor banks

Voltage regulators

Step-down transformers

Description of substation

Number and size of station transformers

LTC/regulator capabilities

Bus arrangement

Potential infrastructure upgrade information

High-level estimate of distribution and substation upgrades (+/- 50%)

Available capacity before major infrastructure upgrades are required

Estimated timeline for construction of infrastructure upgrades

Limiting factors of current infrastructure

Other potential constraints or critical items that may jeopardize project

# Timelines

It is intended that the Study will be performed within the timelines in the current tariff allowed for “Complete Review of All Screens” and “Complete Standard Process Initial Review”.  As such, the Study shall be completed within 25 working days for the both the Expedited and Standard tracks.  Refer to the attached tables for a detailed list of proposed timelines.

Expedited Track Timeline

| Current Expedited Process |  | Proposed Expedited Process |
| --- | --- | --- |
|  |  |  | Pre-Application timeline | w/out Feasibility Study | w/ Feasibility Study |
|  |  |  | Utility provides Pre-Application response | 5 days | 5 days |
|  |  |  | Optional: Developer requests Feasibility Study |  |  |
|  |  |  | Utility sends Feasibility Study cost and agreement |  | 3 days |
|  |  |  | Developer submits payment and returns agreement |  | 3 days |
|  |  |  | Complete review of all screens / Complete Feasibility Study | 20 days | 25 days |
| Application timeline |  |  | full application timeline |  |  |
| Acknowledge Receipt of Application | 3 days |  | Acknowledge Receipt of Application | 3 days | 3 days |
| Review Application for Completeness | 10 days |  | Review Application for Completeness | 10 days | 7 days |
| Complete Review of All Screens | 25 days |  |  |  |  |
| Send executable agreement | 10 days |  | Send executable agreement | 10 days | 10 days |
| Total maximum days | 48 days |  | Total maximum days | 48 days | 56 days |

Standard Track Timeline

| Current Standard Process |  | Proposed standard Process |
| --- | --- | --- |
|  |  |  | Pre-Application timeline | w/out Feasibility Study | w/ Feasibility Study |
|  |  |  | Utility provides Pre-Application response | 5 days | 5 days |
|  |  |  | Optional: Developer requests Feasibility Study |  |  |
|  |  |  | Utility sends Feasibility Study cost and agreement |  | 3 days |
|  |  |  | Developer submits payment and returns agreement |  | 3 days |
|  |  |  | Complete review of all screens / Complete Feasibility Study | 20 days | 25 days |
| Application timeline |  |  | full application timeline |  |  |
| Acknowledge Receipt of Application | 3 days |  | Acknowledge Receipt of Application | 3 days | 3 days |
| Review Application for Completeness | 10 days |  | Review Application for Completeness | 10 days | 7 days |
| Complete Initial Review | 20 days |  |  |  |  |
| Send Follow-on Studies Cost/Agreement | 5 days |  | Send Follow-on Studies Cost/Agreement | 5 days | 5 days |
| Complete Impact Study | 55 days |  | Complete Impact Study | 50 days | 50 days |
| -Completed Detailed Study | 30 days |  | Completed Detailed Study | 30 days | 30 days |
| Send executable agreement | 15 days |  | Send executable agreement | 15 days | 15 days |
| Total maximum days | 138 days |  | Total maximum days | 138 days | 146 days |