## Tracking Data
DG Interconnection Tracking and Reporting Template | [7 empty] | draft 9/10/12
Utility Timelines
Reporting Period: |  | from | 2013-11-01 | to | 2013-11-30
Date Filed: |  | 2013-12-10
* added Complex
Application and Site Information | [6 empty] | Application Receipt |  |  |  |  | Screen Review |  |  |  |  | Supplemental Review |  |  |  |  | Standard Process Initial Review |  |  |  |  | Impact Study |  |  |  |  | Detailed Study |  |  |  |  | IA and Pre-Construction Information |  |  |  |  | Construction |  |  |  |  | Witness Test |  | Authorization and Misc Information
Company Name | City/Town | Facility ID (if any) | ZIP Code | Design Capacity (kW) | Fuel Type (Solar, Wind, etc) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Study Begun | Date Review of Screens Study Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Interconnection Agreement Sent | Estimated In-Service Date | System Modification Required | Expedited/Standard / Complex Project** | Construction Commitment Date | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | NOTES | Date of Info Request | Comm/Indus/Res/Muni | Net Metered? (Y/N)
XYZ | Anytown | X123 | 99999 | 100 | Solar | Circuit A | 2012-09-12 | 2012-09-15 | 3 |  |  | 2012-09-30 | 2012-10-15 | 10 |  |  | 2012-10-25 | 2012-11-14 | 15 |  |  | 2012-12-10 | 2012-12-30 | 14 |  |  | 2013-01-10 | 2013-04-01 | 56 |  |  | 2013-05-01 | 2013-07-10 | 48 | [7 empty] | 2013-09-01 | 2013-11-01 | 43
Cell Columns in current Excel Report
A | D | E | F | G | H |  | L | M | [28 empty] | N | O | P | Q* | [8 empty] | R | S |  |  | Suggested

## Holidays
Holiday List 2012-2014
(official Massachusetts Legal Holidays - Sec of State Office)
New Year’s Day | 2012-01-01
Martin Luther King Jr. Birthday | 2012-01-16
Washington’s Birthday | 2012-02-20
Evacuation Day | 2012-03-17
Patriots' Day | 2012-04-16
Memorial Day | 2012-05-28
Bunker Hill Day | 2012-06-17
Independence Day | 2012-07-04
Labor Day | 2012-09-03
Columbus Day | 2012-10-08
Veterans’ Day | 2012-11-11
Thanksgiving Day | 2012-11-22
Christmas Day | 2012-12-25
New Year’s Day | 2013-01-02
Martin Luther King Jr. Birthday | 2013-01-21
Washington’s Birthday | 2013-02-18
Evacuation Day | 2013-03-17
Patriots' Day | 2013-04-15
Memorial Day | 2013-05-27
Bunker Hill Day | 2013-06-17
Independence Day | 2013-07-04
Labor Day | 2013-09-02
Columbus Day | 2013-10-14
Veterans’ Day | 2013-11-11
Thanksgiving Day | 2013-11-28
Christmas Day | 2013-12-25
New Year’s Day | 2014-01-03
Martin Luther King Jr. Birthday | 2014-01-20
Washington’s Birthday | 2014-02-17
Evacuation Day | 2014-03-17
Patriots' Day | 2014-04-21
Memorial Day | 2014-05-26
Bunker Hill Day | 2014-06-17
Independence Day | 2014-07-04
Labor Day | 2014-09-01
Columbus Day | 2014-10-13
Veterans’ Day | 2014-11-11
Thanksgiving Day | 2014-11-27
Christmas Day | 2014-12-25