## Sheet1
MA DG Working Group--1 Year Implementation/Transition Meeting Plan
| 2012: |  |  | 2013:
| October | November | December | January | February | March | April | May | June | July | August | September
1) Redline Tariff (by October 31) | bar: 2012: October
2) Planning for DG Technical | bar: 2012: November to 2012: December
Standards Work Group (by January)
3) Information Tracking/Reporting (Initial) | bar: 2012: November to 2012: December
4) On-going Upgrades Information Tracking/Reporting (Initial) | bar: 2013: April to 2013: May
4) Central Administrator/ | bar: 2013: February to 2013: March
Online Applications (6 months)
5) Insurance & Tax Mark-up (2 months) | bar: 2012: November
6) Initial Applicant Withdrawl (4 months) | bar: 2012: December to 2013: January
7) Trainings and Online Modules (6 months) | bar: 2013: January to 2013: March
8) Outside Engineers (1 year) | bar: 2013: July to 2013: September
9) Accessible GIS (1 year) | bar: 2013: July to 2013: September
10) Dealing with Stacked Applications thru Group Study Process or other means (3-6 months) | bar: 2013: January to 2013: April
12) Standardized Customer/Utility | bar: 2013: June; 2013: August to 2013: September
Communications (12 months)
12) Landowner Agreement | bar: 2013: May to 2013: June
|  | November | December | January | February | March | April | May | June | July | August | September
Proposed Date: | 16 | 15 | 11 | 22 | 19 | 14 | 17 | 16 | 20 | 18 | 20 | 18
Face to Face (FtF) (day-long)/ | FtF | CC | FtF | CC | FtF | CC | FtF | CC | FtF | CC | FtF | FTF
Conference Call (CC) (2-3 hours) | 9-4 | 9-12 | 9-4 | 9-12 | 9-4 | 9-12 | 9-4 | 9-12 | 9-4 | 9-12 | 9-4 | 9-4